## Communication Plan Template
|  |  | No. of stakeholders | 14
Communication Plan for Program ABC |  |  | No. of communication channels | 91
Rev Date: 11-7-2013
Message | Stakeholders | Vehicle | Frequency | Created by | Sender | Due Date | Notes
Program Update - leadership | VP & GM | Meeting | Monthly | Champion/ Program Mgr | Champion/ Program Mgr | TBD | Program status on active projects
Director - Drives
Bus Proc Imp Mgr
Program update - project level | Mgr Lean Project | Meeting | Monthly | Program Mgr | Project Mgr | Tuesdays @9:00am CT | Each team member provides update on assigned projects that are intended to deliver program benefits
Proj Mgr Sourcing
LSS Champion
Mgr Cont Eng
Proj Engr Eng Serv
Top project meetings | Cross functional support | Meeting | Weekly/Bi-weekly | Project Mgr | Project Mgr | per meeting
Engineering change Reviews | Quality | SAP documents | As needed | Project Mgr | Engineering Change Coordinator | Prior to weekly ECN meeting | Engineering change processing requires engagement of the indicated stakeholders.
Prod Certification
Product Management
New Product Mfg
SME discussions | Subject Matter Experts | Email | As needed | Project Mgr | Project Mgr | per email
What are the specifics that need to be communicated. Could be a report on metrics, project update, general information, etc. | Who you will need to communicate with. Could be multiple people at various levels. | Email, Voicemail, Webex, Status updates in meetings, etc | Will this be daily, weekly, monthly, quarterly and if so when. | Who creates the communication. | Who will do the communicating. Might not be the team lead, but stakeholders should know why that person is sending the communication. | When communication needs to be sent out.
Note on E2: John M. Fico: Reference PMBOK guide Fifth Edition, p. 292, for formula